NPS DSC Division 1 Specifications

National Park Service (NPS) - Denver Service Center (DSC) | 1-8-24

By using NPS DSC Division 1 Specifications, you acknowledge you read, understand,
and will format edits according to NPS DSC Division 1 Specifications Instructions.

<Insert Park and Project Management Information System (PMIS) number>

SECTION 01 32 16 – CONSTRUCTION SCHEDULE

GENERAL

SUMMARY

Section consists of Construction Schedule requirements including:

Adjust list to suit Project.

Schedule of Values

Construction Schedule Requirements.

Construction Schedule Updates.

Time Impact Analysis.

Purpose: The Construction Schedule ensures adequate planning, coordination, scheduling, and reporting during execution of the work by the Construction Contractor. It shall assist the Construction Contractor and Contracting Officer (CO) in monitoring the progress of the work, evaluating proposed changes, and processing Construction Contractor's monthly progress payments. It shall include the dates in the contract, phases, milestones, occupancies, holidays, weather consideration, a critical path, and the requirements of this section.

DEFINITIONS

Activity: A discrete part of a project identified for planning, scheduling, monitoring, and controlling the construction project. Activities included in a construction schedule consume time and resources.

Critical activities are activities on the critical path. They start and finish on the planned early start and finish times.

Predecessor Activity: An activity that precedes another activity in the network.

Successor Activity: An activity that follows another activity in the network.

Cost Loading: Allocation of the Schedule of Values for completion of an activity as scheduled. The sum of costs for all activities must equal the total Contract Sum, unless otherwise approved by the Contracting Officer.

Critical Path Method (CPM): Method of planning and scheduling a construction project where activities are arranged based on activity relationships. Network calculations determine when activities can be performed and the critical path of Project.

Critical Path: Longest connected chain of interdependent activities through the network schedule that establishes minimum overall Project duration and contains no float.

Float: Measure of leeway in starting and completing an activity.

Float: Not for the exclusive use or benefit of the Government or Construction Contractor but is jointly owned.

Free Float: Amount of time an activity can be delayed without adversely affecting the early start of the successor activity.

Total Float: Measure of leeway in starting or completing an activity without adversely affecting planned Project completion date.

Resource Loading: Allocation of manpower and equipment necessary for completion of an activity as scheduled.

Fragnet: A partial or fragmentary network that breaks down activities into smaller activities for greater detail.

SUBMITTALS

Electronic Copies: Schedules and reports submitted shall be posted on the NPS project  management and communication software as PDF (portable document format) files. The intent of the Government is to limit the number of printed reports to those determined by the project team as essential.

Schedule of Values: After contract award and before Pre-Construction conference, submit schedule of dollar values based on Contract Price Schedule.

Construction Baseline Schedule: After contract award and before Pre-Construction conference, submit [two] <Insert number> paper copies of baseline schedule, large enough to show entire schedule for entire construction period. Utilize Schedule of Values in preparation of Construction Baseline Schedule.

Critical Path Method (CPM) Reports: Concurrent with CPM schedule, submit [three] <Insert number> paper copies of the following computer-generated reports. For each activity, include activity number, activity description, cost and resource loading, original duration, remaining duration, early start date, early finish date, late start date, late finish date, and total float in calendar days.

Activity Report: List of activities sorted by activity number and then early start date, or actual start date if known.

Logic Report: List of predecessor and successor tasks for activities sorted in ascending order by activity number and then early start date, or actual start date if known.

Total Float Report: List of activities sorted in ascending order of total float.

Construction Schedule Updates: On or before 7th day preceding progress payment request date, submit estimates of percent completion of each schedule activity and necessary supporting data. Provide two paper copies.

Construction Schedule Revisions and Time Impact Analysis: For each Construction Schedule revision, submit [two] <Insert Number> paper copies of a Time Impact Analysis. Incorporate a Fragmentary Network (Fragnet) into currently accepted Construction Schedule demonstrating proposal to incorporate a modification, change, delay, or Construction Contractor request.

QUALITY ASSURANCE

Construction Contractor shall meet with Contracting Officer on day of the preconstruction conference to go over:

Some or most of these review topics should already have been covered before this meeting. Comments should have been generated and sent to the Contractor. Primary focus of this meeting should be dealing with outstanding issues, incorporating comments and timing to receive an acceptable baseline schedule.

Review software limitations, content and format for reports.

Verify availability of qualified personnel needed to develop and update schedule.

Discuss constraints, including [phasing] [work stages] [area separations] [interim milestones] [and] [partial Government occupancy/substantial completions].

Review delivery dates for Government-furnished products.

Review schedule for work of separate Government contracts.

Review time required for review of submittals and re-submittals.

Review requirements for tests and inspections by independent testing and inspecting agencies.

Review time required for completion and startup procedures.

Review time required for obtaining and activating permits.

Review and finalize list of construction activities to be included in schedule.

Review baseline schedule comments, resolve issues and progress on incorporating them

Review procedures for updating schedule.

Discuss reporting requirements and establish protocol for naming and transmitting electronic schedules.

Construction Contractor's Schedule Representative: Before the preconstruction conference, designate an authorized representative to be responsible for preparing and maintaining the Construction Schedule. Submit resume outlining qualifications of Scheduler to Contracting Officer for acceptance. Scheduler shall have prepared and maintained at least 5 previous schedules of similar size and complexity similar to this Contract, demonstrating proficiency of using scheduling software. Authorized representative will be responsible for preparing the Baseline Schedule, required updates, revisions, Time Impact Analyses, and reports.

COORDINATION

Coordinate preparation and processing of schedules and reports with performance of construction activities and with scheduling and reporting of separate Construction Contractors.

Coordinate Construction Baseline Schedule with Schedule of Values, list of subcontracts, Submittals Schedule, progress reports, payment requests, and other required schedules and reports.

In developing Construction Baseline Schedule, ensure Subcontractor’s work at all tiers, and prime Construction Contractor’s work, is included and coordinated.

Secure time commitments for performing critical elements of work from parties involved.

Coordinate each construction activity in network with other activities and schedule in proper sequence.

PRODUCTS

SCHEDULE OF VALUES

Breakdown each lump-sum item into component work activities used in the schedule for which progress payments may be requested. Work activities broken out within schedule of values shall be integrated into and made a logical part of the construction baseline schedule. Total costs for the component work activities shall equal contract price for that lump-sum item. Contracting Officer may request data to verify accuracy of dollar values. Include mobilization, general condition costs, overhead and profit in the total dollar value of unit price items and in the component work activities for each lump-sum item. Do not include mobilization, general condition costs, overhead or profit as a separate item.

Do not break down unit price items. Use only the contract price for unit price items.

Total cost of all items shall equal the contract price. The Schedule of Values will form the basis for progress payments and the Construction Schedule.

CONSTRUCTION SCHEDULE REQUIREMENTS

Construction Baseline Schedule: Prepare Construction Baseline Schedule using a computerized, cost and resource-based, time-scaled Critical Path Method network analysis diagram for the Work.

Federal Acquisition Regulation - FAR 2.101 states, "Day means, unless otherwise specified, a calendar day." Please be consistent and specific throughout specifications regarding notifications, review times, etc.

Develop and finalize Construction Baseline Schedule so it can be accepted for use no later than [30] <Insert number> days after date established for the Notice of Award.

Failure to include any work item required for performance of this Contract shall not excuse Construction Contractor from completing work within applicable completion dates, regardless of Governments acceptance of schedule.

Establish procedures for monitoring and updating Construction Baseline Schedule and for reporting progress. Coordinate procedures with progress meeting and payment request dates.

Construction Baseline Schedule Preparation: Prepare a list of all activities required to complete the Work. Using preliminary Critical Path Method network diagram, prepare a skeleton network to identify probable critical paths.

Activities: Indicate estimated duration, sequence requirements, and relationship of each activity in relation to other activities.

Critical Path Activities: Identify critical path activities, including those for interim completion dates. Scheduled start and completion dates shall be consistent with Contract milestone dates.

Processing: Process data to produce output data on a computer-drawn, time-scaled network. Revise data, reorganize activity sequences, and reproduce as often as necessary to produce the Critical Path Method schedule within the limitations of the Contract Time.

Show sequence and interdependence of activities required for completion of work. Ensure work sequences are logical and Construction Baseline Schedule shows a coordinated plan of the work.

Resource loading of each activity shall include personnel by labor category and equipment type and capacity proposed to complete the activity in duration shown.

Consider seasonal weather conditions in planning and scheduling work influenced by high and low ambient temperatures, wind, or precipitation to ensure completion of work within contract time.

Time Frame: Proposed duration assigned to each activity shall be Construction Contractor's best estimate of time required to complete activity considering the scope and resources planned for activity.

An early finish date may be shown but the late finish date shall be same date as last day of contract period. An early completion schedule shall contain:

Insert an activity titled "Project Float" as a successor to last activity in early project completion schedule network.

Add a milestone titled "Contract End Date" as a successor to the activity "Project Float".

Add duration to the activity "Project Float" as required so the milestone "Contract End Date" equals the last day of Contract Period.

Contract completion date shall not be changed by submission of a schedule that shows an early completion date.

Construction Contractor shall limit use of lead or lag duration’s between schedule activities.

Project Calendars: Develop and incorporate the following calendars:

Administrative Calendar: Include calendar based on a 7-day week to be used on activities based on calendar days. Apply this calendar to administrative tasks or other tasks not affected by non-working days (Federal Holidays, weather, etc.).

Project Calendar: Include calendar based on planned work week for the project. Include Federal Holidays, weekends, and non-workdays indicated in contract documents. Apply this calendar to activities not anticipated to be affected by weather. Be clear when identifying number of work days in work week.

Weather Calendar: Utilize Project Calendar and show anticipated normal downtime related to weather as non-working time. Weather days shall be based on data for local area from a reliable source like the National Oceanic and Atmospheric Administration (NOAA), National Park Service records, or source acceptable to Contracting Officer. Apply this calendar to activities anticipated to be affected by weather.

Revise first subparagraph below to suit Project. Long activity durations provide less detail and, therefore, less information with which to manage a project. As an alternative to specifying activity duration, indicate minimum and maximum number of activities, which will result in a similar effect.

Activity Duration: Define so no activity is longer than [14] <Insert number> days, except for non-construction activities including mobilization, shop drawings and submittals, fabrication and delivery of materials and equipment.

Procurement Activities: Include procurement process activities for long lead items and major items, requiring a cycle of more than 60 calendar days, as separate activities in the schedule. Procurement cycle activities can include submittals, approvals, purchasing, fabrication, and delivery.

<Insert list of major items or pieces of equipment.>

Submittal Review Time: Include review and re-submittal times indicated. Coordinate submittal review times in Construction Baseline Schedule.

Startup and Testing Time: Include not less than <Insert number> days for startup [and] testing [and commissioning activities].

Substantial Completion: Allow time for Government administrative procedures necessary for certification of Substantial Completion. (For more information, refer to Specification 01 77 00 "Closeout Procedures.")

Constraints: Include constraints and work restrictions indicated in Contract Documents and as follows in schedule and show how the sequence of Work is affected.

Delete subparagraphs below not applicable.

Phasing: Arrange list of activities on schedule by phase.

Work under More Than One Contract: Include a separate activity for each contract.

Work Restrictions: Show effect of the following on the schedule:

Revise list below to suit Project.

Coordination with existing construction

Limitations of continued occupancies

Uninterruptible services

Partial occupancy before Substantial Completion

Use of premises restrictions

Provisions for future construction

Seasonal variations

Environmental control

Permit provisions

Other Constraints: <Insert additional constraints not indicated elsewhere.>

Work Stages: Indicate important stages of construction for each major portion of the Work.

Subcontract awards

Submittals

Purchases

Mockups

Fabrication

Sample testing

Deliveries

Installation

Tests and inspections

Adjusting

Curing

Retain below when required under Indoor Air Quality (IAQ) provisions of Division 1 sustainable design requirements Section.

Building flush-out.

Building commissioning activities.

Milestones: Include milestones indicated in Contract Documents in schedule, including, but not limited to, Notice to Proceed, Substantial Completion[.] [, and the following interim milestones:]

<Insert additional milestones not indicated elsewhere.>

Joint Review, Revision, and Acceptance:

Within seven calendar days of receiving Construction Contractor's proposed Construction Baseline Schedule, Contracting Officer shall review initial Construction Baseline Schedule.

Within seven calendar days after review, Construction Contractor shall revise and resubmit Construction Baseline Schedule in accordance with comments presented from review.

In the event the Construction Contractor fails to define any element of work, activity, or logic and the Contracting Officer review does not detect this omission or error, such omission or error, when discovered by Construction Contractor or Contracting Officer, shall be corrected by Construction Contractor within seven calendar days and shall not affect contract period.

Upon acceptance of the Construction Baseline Schedule, Contracting Officer saves schedule as a baseline and updates on a monthly basis. Construction schedule update will be used to evaluate Construction Contractor's monthly applications for payment based upon information developed at monthly Construction Schedule update meeting.

Cost Correlation: In the heading of the schedule, provide a cost correlation line, indicating planned and actual costs. On the line, show dollar volume of Work performed as of dates used to prepare payment requests.

Construction Contractor shall assign cost to construction activities on Construction Baseline Schedule. Costs shall not be assigned to submittal activities unless specified otherwise but may, with Contracting Officer’s approval, be assigned to fabrication and delivery activities. Costs shall be included for testing and commissioning activities, operation and maintenance manuals, punch list activities, Project Record Documents, and demonstration and training (if applicable).

Each activity cost shall reflect an accurate value based on the Contract Price Schedule.

Total cost assigned to activities shall equal total Contract Price.

Recovery Schedule: When periodic schedule update indicates Work is [14] <Insert number> or more calendar days behind current accepted schedule, a separate recovery schedule indicating means by which Construction Contractor intends to regain compliance with the schedule shall also be submitted. Indicate changes to working hours, working days, crew sizes, and equipment required to achieve compliance, and date by which recovery shall be accomplished.

Computer Software: Prepare schedules using a program developed specifically to manage construction schedules.

Use Microsoft Project or Primavera, for <Insert current Windows operating system> (Windows 7 and newer.)

EXECUTION

CONSTRUCTION SCHEDULE UPDATES

Progress Meeting Updates: Provide a [2] <Insert number> week look-ahead schedule, derived from the currently accepted schedule, before each weekly progress meeting. Utilize look-ahead schedule to facilitate and take notes on discussions held during progress meeting.

Monthly Schedule Updates:

General: Update Construction Schedule on monthly basis to reflect construction progress and activities throughout entire contract period and until project substantial completion. The status date of each schedule update shall be the 7th day preceding the progress payment request date.

Procedure: Construction Contractor shall meet with Contracting Officer each month at Construction Schedule update meeting to review progress made through the status date of the Construction Schedule update, including dates activities were started or completed and percentage of work completed on each activity started or completed.

Reports: Concurrent schedule revisions, prepare tabulated reports showing:

Edit report requirements according to preferences.

Identification of activities that have changed

Changes in early and late start dates

Changes in early and late finish dates

Changes in activity durations in workdays

Changes in the critical path

Changes in total float or slack time

Changes in the Contract Time

Narrative: Report shall include a brief description of actual progress made during update period; actual and potential delaying activities; impediments to progress; issues related to inclement weather; progress toward established milestones and project float. Report shall include a brief description of work anticipated to be performed in the next month. Minor revisions to the schedule should be identified for evaluation and acceptance or rejection.

As Work progresses, indicate Actual Completion percentage for each activity.

If schedule update shows a late finish date after contract completion date, include:

Known delays

Actions to get back on schedule

Pending modifications

Impediments or constraints affecting progress

Progress Payments: Monthly updating of the currently accepted Construction Schedule shall be an integral part of the process upon which progress payments will be made. If Construction Contractor fails to provide schedule updates or revisions, a portion of the monthly payment may be retained until corrections have been made.

Distribution: Distribute copies of accepted schedule to Contracting Officer, Contracting Officers Representative, Construction Management Representative, Subcontractors, testing and inspecting agencies, and other parties identified by Construction Contractor with a need-to-know schedule responsibility.

Post copies in Project meeting rooms and temporary field offices.

When revisions are made, distribute updated schedules to same parties and post in same locations. Delete parties from distribution when they have completed their assigned portion of the Work.

Construction Schedule Revisions:

Required Revisions: If, as a result of the monthly schedule update, it appears the currently accepted Construction Schedule no longer represents actual prosecution and progress of the work, Contracting Officer will request, and Construction Contractor shall submit, a revision to the Construction Schedule. Construction Contractor may also request reasonable revisions to currently accepted Construction Schedule in event the Construction Contractor's planning for the work is revised. If Construction Contractor desires to make changes, Construction Contractor shall notify Contracting Officer in writing, stating reason for proposed revision. Accepted revisions shall be incorporated into currently accepted Construction Schedule for next monthly schedule update.

Procedure: If revision to currently accepted Construction Schedule is contemplated, Construction Contractor or Contracting Officer shall advise the other in writing at least seven calendar days prior to next monthly schedule update meeting, describing revision and reasons for the revision. Government-requested revisions will be presented in writing to the Construction Contractor, who shall respond in writing within seven calendar days.

Reports: Concurrent with making revisions to schedule, prepare tabulated reports showing:

Identification of activities changed

Changes in early and late start dates

Changes in early and late finish dates

Changes in activity durations in workdays

Changes in critical path

Changes in total float or slack time

TIME IMPACT ANALYSIS FOR CONTRACT MODIFICATIONS CHANGES DELAYS AND CONSTRUCTION CONTRACTOR REQUESTS:

Requirements: When contract modifications or changes are initiated, delays experienced, or Construction Contractor desires to revise currently accepted Construction Schedule, Construction Contractor shall submit to Contracting Officer a written time impact analysis illustrating the influence of modification, change, delay, or Construction Contractor request on contract time.

Time Extensions: Activity delays, resulting in a late completion date projection, shall not automatically mean an extension of contract time is warranted or due to Construction Contractor. It is possible a modification, change, or delay will not affect existing critical path activities or cause non-critical activities to become critical. A modification, change, or delay may result in absorbing a part of available total float that may exist within an activity chain of the Schedule, not causing any effect on contract time. Time extensions will be granted in accordance with terms of contract.

Extension of contract time will be granted only to the extent the equitable time adjustments to activity or activities affected by modification, change, or delay exceeds total (positive or zero) float available on a particular activity.

Procedure: Each time impact analysis shall be submitted within time period stated in a request for proposal, or time period designated under the clauses entitled Changes or Default. In cases where Construction Contractor does not submit a written request for extension of time and a time impact analysis within the designated time, it is mutually agreed that the particular modification, change, delay, or Construction Contractor request does not require an extension of the contract time. Upon acceptance, time impact analysis shall be incorporated into currently accepted Construction Schedule at next monthly schedule update.

Contract Modifications: Prepare time-impact analysis using fragnets to demonstrate effect of proposed change on overall Construction Schedule for each proposed contract modification concurrent with submission.

END OF SECTION 01 32 16