## Instructions
Submittal List with Review Estimate Instructions
National Park Service (NPS) - Denver Service Center (DSC) ¦ 1-27-21
DESIGN SERVICES (Construction Documents (CD) Phase)
Responsible Party: Design Architect/Engineer (A/E)
1 | Enter Park Acronym, Project Management Information System (PMIS) Number, and Project Title.
2 | Record construction submittal requirements. Complete Specification Section, Paragraph Number, and Description sections. Insert additional rows as required for sections containing multiple submittals.
3 | In Requirements section, enter X for submittal requirements where applicable. Insert additional columns as needed under Informational or Action. Refer to Specification Section 01 33 23 for clarification. (Action submittals require Government resposive action and Informational submittals do not.) Division 1 Specifications submittals are Information submittals.
4 | Attach black and white version to Specification Section 01 33 23 in project manual. Delete instructional note on top of page.
CONSTRUCTION SERVICES (Construction Phase)
Responsible Party: Construction Contracting Officer Representative (COR)
1 | Use Submittal List submitted with Final Construction Documents. Copy/paste submittal information into Submittal List with Review Estimate Template. If amendments issued, adjust submittal requirements as necessary.
2 | Attach this template to Architect/Engineer (A/E) Construction Services Scope of Services.
3 | Use Review Estimate to estimate time required for Architect/Engineer to accomplish Action submittal reviews. Enter estimated whole or partial number of hours per discipline.
4 | Add discipline heading column as required.
5 | Use total number of hours per discipline at bottom of template and apply hourly rates listed in Indefinite Delivery/Indefinite Quantity (IDIQ) contract (using appropriate option period rates) to formulate Government estimate for submittal reviews.
6 | Use information from this template to negotiate submittal review portion of Architect/Engineer Construction Services task order.
7 | Provide template to Construction Management Representative (CMR) to show submittals they are responsible for and submittals to be forwarded to the Architect/Engineer. All Informational submittals will be reviewed by Construction Management Representative.
Responsible Party: Architect/Engineer (A/E)
1 | Indicate level of effort required for each Action submittal review by entering number of whole or partial hours for each discipline under Architect/Engineer Review Time section.
2 | All Informational submittals will be reviewed by Construction Management Representative (CMR).
3 | Use total number of hours per discipline at bottom of template and apply hourly rates listed in Indefinite Delivery/Indefinite Quantity (IDIQ) contract (using appropriate option period rates) to formulate estimate.
4 | Use this estimate to negotiate submittals review portion of Architect/Engineer Construction Services portion of the task order.

## Template
Submittal List with Review Estimate Template
National Park Service (NPS) - Denver Service Center (DSC) ¦ 1-27-21
|  | SUBMITTAL LIST | [8 empty] | ACTION SUBMITTAL
REVIEW ESTIMATE
Park Acronym/Project Management Information System (PMIS) Number: | [10 empty] | (Complete this portion for Architect / Engineer (A/E)
Project Title: | [10 empty] | construction service task order negotiation.)
|  | SUBMITTAL |  |  | REQUIREMENTS | [5 empty] | ARCHITECT / ENGINEER REVIEW TIME
[5 empty] | (Indicate with X) | [5 empty] | (Indicate in whole or partial hours.)
|  |  | INFORMATIONAL |  |  |  | ACTION
SPECIFICATION SECTION | PARAGRAPH NUMBER | DESCRIPTION | CERTIFICATIONS OR LABORATORY TESTS | REPORTS OR CALCULATIONS OR PLAN | MANUFACTURER DATA AND INSTRUCTIONS | OTHER | SAMPLES | SHOP DRAWINGS | MANUFACTURER DATA AND INSTRUCTIONS | OTHER |  | ARCHITECT | CIVIL ENGINEER | STRUCTURAL ENGINEER | MECHANICAL ENGINEER | ELECTRICAL ENGINEER | PROJECT MANAGER COORDINATION | LANDSCAPE ARCHITECT
[11 empty] | Total: | 0 | 0 | 0 | 0 | 0 | 0 | 0